E-Learning @ Valley School, 2010

|  | PRIORITIES | WHAT/HOW? | WHEN? | WHO? |
| --- | --- | --- | --- | --- |
| Pedagogy (Teacher Learning) | Collect teacher data - Cluster | ICT Cluster Baseline Survey Q – ‘What e-learning or ICT have you done in your class last year? In your own life?’ – Survey Monkey | Week 6 professional learning session | David Maureen |
|  | Collect teacher data - School | Slideshare – Jacquie Sharpe “A Whole New Way of Teaching & Learning” | Week 8 professional learning session | Maureen Roger |
|  | Integrate e-learning into planning | Select ONE e-learning tool to integrate into Term 2 planning (e.g. Wordle, Kid Pix). Use information from Survey Monkey. | Week 8 professional learning session | Maureen Nicky |
|  | Develop a collection of e-learning tools for classroom use | As above | On-going | Maureen to co-ordinate |
|  | Further develop Inquiry planning & learning | Visit Wesley Intermediate to view their ‘SUCCESS’ Inquiry Programme in action (Nicky, Maureen, Jenny, Roger, Tony). Nicky to email. | Email Monday 8th March | Nicky |
|  | Share successes and struggles | Invite teachers onto Principal’s Wiki to read messages, share ideas and add feedback on staff meetings/learning. | Week 8 professional learning session | Roger Maureen |
| Infrastructure (Equipment, systems etc) | Inclusion of 5 data projectors for Rms 1-5 | These have been purchased and installed. Teachers are integrating them into classroom programmes. | Term 1 | Rms 1-5 teachers |
|  | Inclusion of x6 computers in each of Rms 1-5 | These have been purchased and installed. Teachers are integrating them into classroom programmes. | Term 1` | Rms 1-5 teachers |
|  | Purchase x10 digital cameras | x1 each in Rms 1-5 x5 for other classes | Term 1 | Roger |
|  | Purchase x4 USB microphones | Room 4 is to trial this equipment before purchasing more. | Term 1 & 2 | Maureen |
|  | Funding for future purchases | Talk with Val regarding applying for funding. | Term 1 & 2 | Roger Val |
|  | Rules for new technology and use of | Devise rules for: - Placement of equipment (computers) - Internet safety (on-line discussions, photos, names, working on the web, validity of information…) - Wiki rules | Term 2 | Maureen Roger Nicky |
|  | Explore new technologies for future purchasing? | Visit schools to view e-learning in action - St Joseph’s: Interactive & Mimio boards - Pukekohe Intermediate: Digital Classroom | Week 6 & 7 | Nicky Maureen Roger |